## Roadmap
N.B. For planning purposes only, all dates and content subject to change - Information as known to EBA IT as of | [6 empty] | 2016-02-18
Information from EBA oversight or regulation should be assumed to take precedence
Dictionary / DPM Version | Public Draft Taxonomy Release Date planned (finalised) | Content | [5 empty] | Expected Reporting Dates |  |  | Specific Reporting Versions
[8 empty] | Expected notional file content date | Expected Last Reporting Date -> NCA | Expected Final remittance date -> EBA | Monthly |  |  | Quarterly |  |  | Annually
|  | COREP | FINREP | Asset Encumbrance | Fundings plans | Benchmarking |  |  |  |  | COREP |  |  | COREP OF, LE, LR, NSFR | FINREP Financial Reporting | AE Asset Encumbrance | FP Funding Plans | SBP Benchmarking
[11 empty] | LCR | LCR_DA | AMM |  |  |  |  | IMV | Main
2.0 | 09/2013 (02/12/2013) | COREP 2.0.1 | FINREP 2.0.1 |  |  |  |  | 2015-05-31 | 2015-06-15 | 2015-06-29 | 2.0.3
|  |  | Unused |  |  |  |  | 2015-06-30 | 2015-07-15 | 2015-07-29 | 2.1.0
2.1 | 03/2014 (08/07/2014) | COREP 2.0.2 | FINREP 2.1.0 | AE 1.0.0 |  |  |  |  | 2015-08-11 | 2015-08-25 |  |  |  | 2.1.0 | 2.1.2 | 1.0.1
|  | Amendments | Amendments FBE/NPE | Unused |  |  |  |  | 2015-09-30 | 2015-11-15 | [6 empty] | 1.0.2
[8 empty] | 2015-07-31 | 2015-08-17 | 2015-08-31 | 2.1.0
2.2 | 08/2014 (18/08/2014) | COREP 2.0.3 | FINREP 2.1.1 | AE 1.0.1 | FP 1.0.0 |  |  | 2015-08-31 | 2015-09-15 | 2015-09-29 | 2.1.0
|  | Amendments | Amendments | Amendments | Unused |  |  | 2015-09-30 | 2015-10-15 | 2015-10-29 | 2.1.0
[9 empty] | 2015-11-11 | 2015-11-25 |  |  |  | 2.1.0 | 2.1.2 | 1.0.1
[8 empty] | 2015-10-31 | 2016-04-11 | 2016-04-25 | [7 empty] | 1.0.1
2.3 (2015-A) | Q4/2014 (02/03/2015) | COREP 2.1.0 | FINREP 2.1.2 |  | FP 1.0.1 | SBP 1.0.0 |  | 2015-10-31 | 2015-11-16 | 2015-11-30 | 2.1.0
|  | ALM Amendments | Amendments |  | Amendments Unused | New Reporting Unused |  | 2015-11-30 | 2015-12-15 | 2016-01-04 | 2.1.0
[8 empty] | 2015-12-31 | 2016-01-15 | 2016-02-01 | 2.1.0
[9 empty] | 2016-02-11 | 2016-02-25 |  |  |  | 2.1.0 | 2.1.2 | 1.0.1
2.3.1 (2015-A-1) | (08/05/2015) |  |  |  | FP 1.0.2 | SBP 1.0.1 |  |  | 2016-03-31 | 2016-04-30 | [6 empty] | 1.0.2
2.3.2 (2015-A-2) | (07/2015) |  | 2.1.3 (Ind) | [5 empty] | 2016-04-11 | 2016-04-25 | [8 empty] | 1.0.1
[8 empty] | 2016-01-31 | 2016-02-15 | 2016-02-25 | 2.1.0
2.4 (2015-B) | Q3/2015 | COREP 2.2.0 | FINREP 2.1.4 |  |  | SBP 1.0.2 |  | 2016-02-29 | 2016-03-15 | 2016-03-25 | 2.1.0 |  | 2.1.0
| (09/09/2015) | LR, LCR Changes | Minor correction |  |  | True multicurrency |  | 2016-03-31 | 2016-04-15 | 2016-04-25 | 2.1.0
|  | QA 1042 - Multicurrency | [6 empty] | 2016-05-12 | 2016-05-26 |  |  | 2.1.0 | 2.1.0 | 2.1.2 | 1.0.1
|  | Unused | Unused |  |  | Unused |  | 2016-04-30 | 2016-05-16 | 2016-05-26 | 2.1.0 |  | 2.1.0
2.4.1 (2015-B-1) | 02/2016 | 2.2.1 | 2.1.4.1 |  |  | 1.0.2.1 |  | 2016-06-30 | 2016-07-15 | 2016-07-25 | 2.1.0 |  | 2.1.0
[9 empty] | 2016-05-12 | 2016-05-23 |  |  |  | 2.1.0 | 2.1.2 | 1.0.1
2.5 (2016-A) | Q1/2016 | COREP 2.2.2 | FINREP 2.1.5 | AE 1.0.2 | FP 1.0.3 | SBP 1.0.3 |  | 2016-07-31 | 2016-08-15 | 2016-08-25 | 2.1.0 |  | 2.1.0
| (02/2016) | Changes to align with CCB disclosure requirements | Changes regarding GAAP reporters | Implement omitted validation rules | minor corrections | Segregation of portfolio reporting by risk type |  | 2016-08-31 | 2016-09-15 | 2016-09-26 | 2.1.0 |  | 2.1.0
First reference date for "2.4" line uncertain - commencement is "6 months after publication of ITS in OJEU"
[8 empty] | 2016-09-30 | 2016-10-17 | 2016-10-27 | 2.2.1 | 2.2.1 | 2.2.1
[9 empty] | 2016-11-11 | 2016-11-25 |  |  |  | 2.2.1 | 2.1.4.1 | 1.0.1
2.6 (2016-B) | Q4/2016 | Trading Book Review, LE Review, SME, Mortgage Exposure, Prudent Valuation, Credit Risk changes (LCR Corrigendum?) | Initial IFRS 9 changes (Probably unused) |  |  | Changes to Benchmarking |  | 2016-10-31 | 2016-10-31 | 2016-11-10 | 2.2.1 | 2.2.1 | 2.2.1
[8 empty] | 2016-11-30 | 2016-11-30 | 2016-12-12 | 2.2.1 | 2.2.1 | 2.2.1
[8 empty] | 2016-12-31 |  |  | 2.2.2 | 2.2.2 | 2.2.2 | 2.2.2 | 2.1.5 | 1.0.2 | 1.0.3 | 1.0.2 | 1.02
Outline Future Working Assumptions
|  | EBA Modelling Review. Possibly also deposit guarantee schemes, interbank deposits, bank recovery and resolution data collection. | [5 empty] | 2017-06-30
2.7 (2017-A) | Q1/2017 | AMM? | IFRS 9 Corrections? |  |  |  |  | 2017-12-31
[8 empty] | Q1 2018 | [6 empty] | IFRS9
Italics = to be confirmed / longer term
FBE: Forbearance
NPE : Non Performing Exposures
IMV: Initial market valuation (part of BM)
SBP: Benchmarking portfolio asssessment (Internal models)
AMM (ALM) : Additional liquidity Monitoring Metrics
Formulas:
Expected Last Reporting Date -> NCA = WORKDAY([Expected Reporting Dates]+14,1)
Expected Last Reporting Date -> NCA = WORKDAY([Expected Reporting Dates, row above]+41,1)
Expected Final remittance date -> EBA = [Expected Reporting Dates]+30
Expected Final remittance date -> EBA = WORKDAY([Expected Reporting Dates]+29,1)
Note on I3: ojones: In general dates determined by legal texts are uncertain until final adoption of said texts and publication in e.g. Official Journal of European Union
Note on I4: ojones: Fill colour indicates DPM version to be used for this report. "File content" date is the date to be used for the content of XBRL instant elements for all facts, and in file name when submitting to ESP system. This is usually the same concept referred to as the "reference date".
Note on J15: ojones: Reporting remittance dates uncertain, pending adoption of ITS by commission and publication in OJEU
Note on K15: ojones: Reporting remittance dates uncertain, pending adoption of ITS by commission and publication in OJEU
Note on F20: ojones: Entry Point split to IND and CON variants
Note on G20: ojones: Entry Point split to IND and CON variants
Note on D21: ojones: Added "Individual" consolidation (i.e. Solo) report, mutually compatible with DPM 2.3(.1 )/ FINREP 2.1.2 in all other respects/for all other reports.
Note on J21: ojones: Reporting remittance dates uncertain, pending adoption of ITS by commission and publication in OJEU
Note on K21: ojones: Reporting remittance dates uncertain, pending adoption of ITS by commission and publication in OJEU
Note on N23: ojones: First reference date for Additional liquidity monitoring metrics is uncertain, pending decision of European Commission and publication by them of ITS in OJEU
Note on C27: ojones: Correction (missing table in COREP CON report)
Note on D27: ojones: in place "instance compatible" correction of erroneous validation rule implementation
Note on G27: ojones: in place "instance compatible" correction of erroneous validation rule implementation